## Slide 1
Introduction – Margaritaville Beach Hotel
Highlighting some areas on the drawings and isometric view using colors and writing the sequence or dates to simplify which building takes place first .
    Critical Path Analysis
    Structural Work Sequence
    Façade Work Sequence
    Landscape Sequencing
Project General Information :
    Project Start (NTP) : Dec,01-2018
    Project Finish :Sep,16-2020
    Project Total Duration: (X) Working Days
    Project Total Duration: (X) Calendar Days

## Slide 2
NTP
Project Byout / Subcontractor award - Project Start
Foundation / Piles
Superstructure / Area A – [ 1st Floor through Roof Floor]
North Facade /
[ Densglass Sheathing through Scaffolding Removal]
(10) Days - Lag
Install Storm Tech
Landscape (North Side)/
[ Clearing & Grading through Punch]
Final Inspection
Project Finish
Critical Path Analysis – Margaritaville Beach Hotel
Start : Dec,01-2018
Start : Dec,03-2018
Finish : Dec,31-2018
Duration : 18 days
Start : May,19-2018
Finish : Jul,06-2018
Duration : 30 days
Start : Dec,03-2018
Finish : Dec,31-2018
Duration : 18 days
Finish : Sep,16-2018
Start : Jan,25-2019
Finish : May,08-2019
Duration : 66 days
Start : May,06-2019
Finish : Nov,26-2019
Duration : 121 days
Start : Dec,16-2019
Finish : May,18-2020
Duration : 97 days
Start : Jul,07-2020
Finish : Aug,12-2020
Duration : 25 days

## Slide 3
Structural Work (Sequence) – Margaritaville Beach Hotel
Start : Jan,25-2019
Finish : May,08-2019
Duration : 66 days
Start : Jan,25-2019
Finish : May,08-2019
Duration : 66 days
1st LVL – Verticals Only
2nd LVL
3rd LVL
4th LVL
5th LVL
6th LVL
7th LVL
8th LVL
Roof Slab
S.O.G Will start after Completion of 5th LVL Structural work

## Slide 4
Facade Work (Sequence) – Margaritaville Beach Hotel
E
N
S
W
Once we finish structural work till roof then we go with East Façade :
Start : Nov,27-2019
Finish : May,01-2020
Duration : 97 days
Once we finish structural work till roof then we go with South Façade after 20 days :
Start : Jan,02-2020
Finish : Jun,03-2020
Duration : 97 days
Once we finish structural work till roof then we go with North Façade after 10 days :
Start : Dec,16-2019
Finish : May,18-2020
Duration : 97 days
Once we finish structural work till roof then we go with West Façade after 30 days :
Start : Jan,17-2020
Finish : Jun,18-2020
Duration : 97 days
Once we finish structural work till roof then we go with North Façade after 10 days :
Start : Dec,16-2019
Finish : May,18-2020
Duration : 97 days
***Critical***

## Slide 5
Landscape (Sequence) – Margaritaville Beach Hotel
E
N
S
W
Once we Remove Scaffolding of East Façade we go with tower crane removal & Scaffolding Removal (Start : April,30-2020
Finish : May,01-2020
Duration : 02 days) then we go through Landscape (East Side)
Start : May,04-2020
Finish : Jul,29-2020
Duration : 55 days
Once we Remove Scaffolding of South Façade then we go through Landscape (South Side)
Start : Jun,04-2020
Finish : Jul,13-2020
Duration : 25 days
Once we Remove Scaffolding of North Façade we go with Storm Tech (Start : May,19-2018
Finish : Jul,06-2018
Duration : 30 days) then we go through Landscape (North Side) starting with Storm Tech. with Lag 20 days
Start : Jul,07-2020
Finish : Aug,12-2020
Duration : 25 days
Once we Remove Scaffolding of West Façade then we go through Landscape (West Side)
Start : Jun,19-2020
Finish : Jul,29-2020
Duration : 25 days
Once we Remove Scaffolding of North Façade we go with Storm Tech (Start : May,19-2018
Finish : Jul,06-2018
Duration : 30 days) then we go through Landscape (North Side) starting with Storm Tech. with Lag 20 days
Start : Jul,07-2020
Finish : Aug,12-2020
Duration : 25 days
***Critical***