## Slide 1: Resilience Protection of the Steinway Tube Under River Contracts# (C-34924/ E-40848/ W-32574)
Baseline Schedule Presentation
The Metropolitan Transportation Authority Acting by the New York City Transit Authority
Main Contractor:
Rising Sun Construction
CPM Scheduling Consultant: HSE CONTRACTORS INC

## Slide 2: Content
Project Information
Project Description & Type of work
Constraints
Resources
S-Curve

## Slide 3: Project Information
NTP : December 19, 2022
Substantial Completion : April 17, 2025
Project Duration : 851 Calendar Days
Project value : 25,838,246$
Project location : NEW YORK

## Slide 4: 2. Project Description & TYPE OF WORK
(Contract C-34924) Sandy mitigation: Steinway portal borough of queens.
(Contract E-40848) Pumping System Improvement in midtown Steinway tube in the borough of Manhattan and queens.
(Contract W-32574) Police radio systems: Shaft 4 BDA enclosure.
Resiliency Protection of the Steinway under the river tube in the boroughs of Manhattan and queens consists of:
Description | Duration | Start | Finish | Budgeted Total Cost
Sandy Mitigation Steinway Work | 425 | 03-Jul-23 | 16-Mar-25 | $9,057,592.00
Pumping System Improvement Work | 288 | 21-Oct-23 | 16-Dec-24 | $8,969,018.00
Police radio and antenna equipment | 353 | 27-Jun-23 | 21-Nov-24 | $1,029,840.00
Chart: 
| Sandy Mitigation steinway Work | Pumping System Improvement Work | Police radio and antenna equipment
 | 9057592 | 8969018 | 1029840

## Slide 5: (Contract C-34924) Sandy mitigation: Steinway portal borough of queens
Start date : 03-Jul-2023
Finish date : 16-Mar-2025
(Contract C-34924) consists of :
Concrete Flood Wall
Flood Gates Barriers
Cantilever Flood Wall
Removal of existing retaining wall at North and South elevations
Steel Catwalk
Flex Gates work
Steel Catwalk
Flex Gates work
Removal of existing retaining wall
Concrete Flood Wall
Flood Gates Barriers (WFD 006)

## Slide 6: (Contract C-34924) Sandy mitigation: Steinway portal borough of queens
Chart: 
| Concrete Flood Wall | Flood Gates Barriers | Cantilever Flood Wall | Removal of existing retaining wall | Steel Catwalk | Flex Gates work
 | 3295960 | 71000 | 125600 | 305000 | 432650 | 4785882
Type of work | Duration | Start | Finish | Budgeted Total Cost
Concrete Flood Wall | 304 | 28-Aug-23 | 13-Nov-24 | $3,295,960.00
Flood Wall | 95 | 28-Jun-24 | 13-Nov-24 | $1,005,060.00
Cantilever Flood Wall | 14 | 28-Oct-23 | 19-Nov-23 | $125,600.00
Removal of existing retaining wall | 51 | 28-Oct-23 | 14-Jan-24 | $305,000.00
Steel Catwalk | 5 | 20-Jan-24 | 28-Jan-24 | $432,650.00
Flex Gates work | 5 | 08-Mar-25 | 16-Mar-25 | $4,785,882.00

## Slide 7: Concrete Flood Wall work
Piles starts
Pile Cap
Flood Wall
Type of work | Duration | Start | Finish | Budgeted Total Cost
Piles | 101 | 28-Aug-23 | 24-Jan-24 | $1,485,000.00
Pile Cap | 108 | 25-Jan-24 | 27-Jun-24 | $805,900.00
Flood Wall | 95 | 28-Jun-24 | 13-Nov-24 | $1,005,060.00
Chart: 
| Piles | Pile Cap | Flood Wall
Budgeted Total Cost | 1485000 | 805900 | 1005060

## Slide 8: (Contract E-40848) Pumping System Improvement in midtown Steinway tube in the borough of Manhattan and queens.
Start date : 21-Oct-2023
Finish date : 16-Dec-2024
(Contract E-40848) consists of :
Structural Work
Mechanical and Plumbing work
Electrical Work
Instrumentation and Control
Communication Work
Pump Room 3229,3228,PR 3227
C1 track Manhattan
C2 Track Queens
Shaft 4, Shaft 2.

## Slide 9: Pumping System Improvement Work
Chart: 
| Structural Work | Mechanical and Plumbing | Electrical Work | Instrumentation and Control | Fire Alarm | Communication Work
Budgeted Total Cost | 795760 | 3288400 | 3357652 | 962316 | 99700 | 465190
Type of work | Duration | Start | Finish | Budgeted Total Cost
Structural Work | 212 | 13-Jan-24 | 17-Nov-24 | $795,760.00
Mechanical and Plumbing | 96 | 21-Oct-23 | 12-Mar-24 | $3,288,400.00
Electrical Work | 269 | 21-Oct-23 | 16-Dec-24 | $3,357,652.00
Instrumentation and Control | 19 | 19-Oct-24 | 17-Nov-24 | $962,316.00
Fire Alarm | 20 | 08-May-24 | 05-Jun-24 | $99,700.00
Communication Work | 60 | 13-Mar-24 | 17-Nov-24 | $465,190.00

## Slide 10: Pump Rooms (3229,3228,3227)
Pump Room (3229)
Pump Room (3228)
Pump Room (3227)

## Slide 11: C1 track Manhattan

## Slide 12: C2 Track Queens

## Slide 13: Shaft 4, Shaft 2.

## Slide 14: (Contract W-32574) Police radio systems: Shaft 4 BDA enclosure..
Start date : 27-Jun-2023
Finish date : 21-Nov-2024
(Contract E-40848) consists of :
Concrete Work
Door Hardware
Electrical work
Signal Work
Communication Work

## Slide 15: Police radio and antenna equipment installation and replacement
Type of work | Duration | Start | Finish | Budgeted Total Cost
Concrete Work | 20 | 27-Jun-23 | 25-Jul-23 | $20,000.00
Door Hardware | 60 | 28-Aug-23 | 22-Nov-23 | $36,000.00
Electrical work | 100 | 24-Nov-23 | 17-Apr-24 | $140,140.00
Signal Work | 30 | 18-Apr-24 | 30-May-24 | $40,000.00
Communication Work | 120 | 31-May-24 | 21-Nov-24 | $793,700.00
Chart: 
| Concrete Work | Door Hardware | Electrical work | Signal Work | Communication Work
Budgeted Total Cost | 20000 | 36000 | 140140 | 40000 | 793700

## Slide 16: 3. Constraints
NYC Transit’s Operations Planning (OP) has planned out a series of weekend shutdowns for 2023 and the first month of 2024 based on the overall needs and SOW for contracts along the #7 line. In order to accommodate all the sports events, holiday embargoes as well as each other’s construction needs, all contractors along the #7 Line have been encouraged to share these GOs to carry out their respective work. With the understanding that individual contracts will have their unique need(s).
The followings are the planned GOs by OP so far:
The year 2023: Weeks 43,44,46 &47
The year 2024: weeks 1,2,3,4,43,46,47
The year 2025: weeks 8,9,10,11

## Slide 17: 4. Resources
Resources distribution
Description |  | Jun-23 | Jul-23 | Aug-23 | Sep-23 | Oct-23 | Nov-23 | Dec-23 | Jan-24 | Feb-24 | Mar-24 | Apr-24 | May-24 | Jun-24 | Jul-24 | Aug-24 | Sep-24 | Oct-24 | Nov-24 | Dec-24 | Jan-25 | Feb-25 | Mar-25
Total | Early | 4 | 23 | 10 | 25 | 85 | 51 | 32 | 154 | 77 | 58 | 59 | 85 | 47 | 55 | 35 | 33 | 93 | 172 | 17 |  |  | 13
 | Late |  |  | 8 | 23 | 95 | 53 | 35 | 132 | 50 | 43 | 33 | 39 | 40 | 65 | 62 | 57 | 114 | 201 | 66 |  |  | 13
Carpenter | Early |  |  |  |  | 1 | 1 |  |  |  | 4 | 2 | 2 | 0 | 6 | 2 | 3 | 1 |  |  |  |  | 
 | Late |  |  |  |  | 1 | 1 |  |  |  | 3 | 2 | 2 |  | 5 | 3 | 2 | 2 |  |  |  |  | 
Communication technecian | Early |  |  |  |  |  |  |  |  |  | 2 | 4 | 6 | 3 | 3 | 3 | 3 | 3 | 4 |  |  |  | 
 | Late |  |  |  |  |  |  |  |  |  |  |  | 2 | 2 | 3 | 3 | 4 | 6 | 5 | 4 |  |  | 
Communication technecian GO | Early |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 16 |  |  |  | 
 | Late |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 16 |  |  |  | 
Electrician | Early |  |  | 1 | 5 | 5 | 5 | 5 | 7 | 9 | 5 | 3 |  |  |  |  |  |  | 9 | 11 |  |  | 
 | Late |  |  |  | 2 | 5 | 5 | 5 | 5 | 8 | 8 | 6 | 2 |  |  |  |  |  | 9 | 11 |  |  | 
Electrician GO | Early |  |  |  |  | 3 |  |  | 7 |  |  |  |  |  |  |  |  | 5 | 5 |  |  |  | 
 | Late |  |  |  |  | 3 |  |  | 7 |  |  |  |  |  |  |  |  | 5 | 5 |  |  |  | 
Fire Alarm technician | Early |  |  |  |  |  |  |  |  |  |  |  | 2 | 0 |  |  |  |  |  |  |  |  | 
 | Late |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 | 1 |  |  | 
Flex Gate installer | Early |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0
 | Late |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0
Labor GO | Early |  |  |  |  | 28 | 2 |  | 53 |  |  |  |  |  |  |  |  | 36 | 68 |  |  |  | 
 | Late |  |  |  |  | 28 | 2 |  | 53 |  |  |  |  |  |  |  |  | 36 | 68 |  |  |  | 
Labour | Early | 4 | 20 | 7 | 20 | 44 | 41 | 25 | 81 | 63 | 46 | 46 | 75 | 44 | 45 | 26 | 26 | 48 | 70 | 4 |  |  | 12
 | Late |  |  | 8 | 21 | 48 | 42 | 28 | 63 | 43 | 32 | 22 | 32 | 38 | 55 | 48 | 46 | 66 | 97 | 48 |  |  | 12
Mechanic | Early |  |  |  |  |  |  |  | 3 | 5 | 2 |  |  |  |  |  |  |  |  |  |  |  | 
 | Late |  |  |  |  |  |  |  |  |  |  |  |  |  | 2 | 6 | 3 |  |  |  |  |  | 
Mechanic GO | Early |  |  |  |  | 4 | 2 |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Late |  |  |  |  | 4 | 2 |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Rigger | Early |  |  |  |  |  |  |  |  |  |  |  |  | 0 | 1 |  |  |  |  |  |  |  | 
 | Late |  |  |  |  |  |  |  |  |  |  |  |  |  | 2 |  |  |  |  |  |  |  | 
Steel fixer | Early |  | 3 | 2 |  | 1 | 2 | 2 | 3 |  |  | 4 | 1 |  |  | 3 | 2 |  |  |  |  |  | 1
 | Late |  |  |  | 0 | 6 | 2 | 2 | 3 |  |  | 3 | 2 |  |  | 3 | 3 |  |  |  |  |  | 1
WFD-006 installer | Early |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 | 2 |  |  | 
 | Late |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0 | 2 |  |  | 

## Slide 18: Resources
Resources Profile

## Slide 19: 5. S-curve