## Slide 1: NCDOT Delay Associated with Various Impacts, Including PNG Relocation R-2247EB I-74 Interchange at US 52 NOI# 1 Claim
NCDOT Delay Associated with Various Impacts, Including PNG Relocation R-2247EB I-74 Interchange at US 52 NOI# 1 Claim

## Slide 2: Project analysis slide 2
CONTENTS
CONTENTS
CRITICAL PATH
CONTROLLING ACTIVITIES
REASONS FOR DELAY
PARTIES AGREEMENTS & DISAGREEMENTS
PLANNED SCHEDULE
V.S.
IMPACTED SCHEDULE
WORKING OUT OF
SEQUENCE
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY

## Slide 3: Project analysis slide 3
AGREEMENTS & DISAGREEMENTS
MARKET ANALYSIS
TECHNICAL ANALYSIS
FINANCIAL ANALYSIS
ECONOMIC ANALYSIS
ECOLOGICAL ANALYSIS
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Where the Parties Agree/Disagree
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY

## Slide 4: Project analysis slide 3
ICT # 1 Functional Interchange Compression
MARKET ANALYSIS
TECHNICAL ANALYSIS
FINANCIAL ANALYSIS
ECONOMIC ANALYSIS
ECOLOGICAL ANALYSIS
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
36.8% of Construction Time Lost
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY
The PNG Relocation Impact was 277 days which is about 36.8% of the construction lost time. As the duration of the construction between completion of PNG relocation and functional interchange was 752 days.
277 days

## Slide 5: Project analysis slide 3
Magnitude of FIC Compression
MARKET ANALYSIS
TECHNICAL ANALYSIS
FINANCIAL ANALYSIS
ECONOMIC ANALYSIS
ECOLOGICAL ANALYSIS
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Planned Construction Days from PNG Relocation
to ICT #1 Functional Interchange Open: 752 Days
Days of Delay in PNG Relocation: 277 Days
The planned construction time for the project was 752 days, but there was a delay of 277 days due to the delay of the PNG Relocation. This delay was almost 37% of the planned time. Blythe had to change the order of the work and how it was done.
Unfortunately, it wasn’t possible to make up for all the lost time, so the project took longer than expected.
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY

## Slide 6: Project analysis slide 3
NCDOT Objections to Settlement of the NOI #1Claim as Requested
MARKET ANALYSIS
TECHNICAL ANALYSIS
FINANCIAL ANALYSIS
ECONOMIC ANALYSIS
ECOLOGICAL ANALYSIS
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
NCDOT Objections and Rebuttal
ICT # 1 Functional Interchange Compression
Magnitude of FIC Compression
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY

## Slide 7: Project analysis slide 3
NCDOT Objections to Settlement of the NOI #1Claim as Requested
MARKET ANALYSIS
TECHNICAL ANALYSIS
FINANCIAL ANALYSIS
ECONOMIC ANALYSIS
ECOLOGICAL ANALYSIS
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY

## Slide 8: Project analysis slide 3
NCDOT Objections to Settlement of the NOI #1Claim as Requested
MARKET ANALYSIS
TECHNICAL ANALYSIS
FINANCIAL ANALYSIS
ECONOMIC ANALYSIS
ECOLOGICAL ANALYSIS
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY

## Slide 9
P6 Summary To Show before & after impact
P6 Summary

## Slide 10
The following slides are 3 window analysis before and after the impact
P6 Summary

## Slide 11
Project Duration
01-Oct-18
R-2247 EB Winston-Salem By-pass Schedule Logic
01-Aug-23
Project
Duration
01-Oct-18
PNG Relocation (277) CD
02-Sep-19
04-June-20
Project Duration
Punch List
01-Sep-22
Final Completion
Substantial Completion
Start Date
Start Date
30-Aug-2023
Final Completion
Punch List
03-Aug-22
Substantial Completion
Updated Project Schedule Sep-2019 Before Impact
Phase 1
Ramp C
Phase 1
Y62 Ramp C
Phase 1 Structure 11
Phase 1 Structure 11 Tie In
Phase 3 Structure 6 Tie In
Phase 3 Structure 5
Critical Path
Updated Project Schedule Sep-2019 After Impact
variance= -363 CD delay
Variance = 0 CD delay

## Slide 12
R-2247 EB Winston-Salem By-pass Schedule Logic
Variance = 0 CD delay
Updated Project Schedule Sep-2019 Before Impact

## Slide 13
R-2247 EB Winston-Salem By-pass Schedule Logic
Updated Project Schedule Sep-2019 After Impact
Variance = -363 CD delay

## Slide 14
R-2247 EB Winston-Salem By-pass Schedule Logic
Time Window # A | Schedule Finish Date
Update SEP-2019 before Delays | 01-Sep-22
Update SEP-2019 After Delays | 30-Aug-23
Variance | -363
Table (1) Impact of Delay Events on Project Finish Date Sep-2019 :

## Slide 15
Project Duration
01-Oct-18
R-2247 EB Winston-Salem By-pass Schedule Logic
06-Oct-23
Project
Duration
01-Oct-18
PNG Relocation
(277) CD
02-Sep-19
10-June-20
Project Duration
Extra Work SA 1-20 & 22 (38) CD
Punch List
08-Jun-23
Final Completion
Start Date
Start Date
06-Nov-23
Final Completion
Punch List
10-May-23
Substantial Completion
Extra Work SA 21 (111) CD
17-Jun-23
Updated Project Schedule Jun-2020 Before Impact
10-May-23
Substantial Completion
Updated Project Schedule Jun-2020 After Impact
Variance = -431 CD delay
Variance = -280 CD delay

## Slide 16
R-2247 EB Winston-Salem By-pass Schedule Logic
Updated Project Schedule Jun-2020 Before Impact
Variance = -280 CD delay

## Slide 17
R-2247 EB Winston-Salem By-pass Schedule Logic
Updated Project Schedule Jun-2020 After Impact
Variance = -431 CD delay

## Slide 18
R-2247 EB Winston-Salem By-pass Schedule Logic
Time Window # B | Schedule Finish Date
Update JUNE-2020 before Delays | 08-Jun-23
Update JUNE-2020 After Delays | 06-Nov-23
Variance | -151
Table (2) Impact of Delay Events on Project Finish Date Jun-2020 :

## Slide 19
Project Duration
01-Oct-18
R-2247 EB Winston-Salem By-pass Schedule Logic
15-Sep-23
Project
Duration
01-Oct-18
PNG Relocation
(277) CD
02-Sep-19
10-June-20
Project Duration
Extra Work SA 1-20 & 22 (38) CD
Punch List
18-May-23
Final Completion
Start Date
Start Date
16-Oct-23
Final Completion
Punch List
19-Apr-23
Substantial Completion
Extra Work SA 21 (111) CD
27-May-23
Updated Project Schedule Aug-2020 Before Impact
19-Apr-23
Substantial Completion
Updated Project Schedule Aug-2020 After Impact
Variance = -410 CD delay
Variance = -259 CD delay

## Slide 20
R-2247 EB Winston-Salem By-pass Schedule Logic
Updated Project Schedule Aug-2020 Before Impact
Variance = -259 CD delay

## Slide 21
R-2247 EB Winston-Salem By-pass Schedule Logic
Updated Project Schedule Aug-2020 After Impact
Variance = -410 CD delay

## Slide 22
R-2247 EB Winston-Salem By-pass Schedule Logic
Time Window # C | Schedule Finish Date
Update AUGUST-2020 before Delays | 18-May-2020
Update AUGUST-2020 After Delays | 16-Oct-2020
Variance | -151
Table (3) Impact of Delay Events on Project Finish Date Aug-2020 :

## Slide 23
R-2247 EB Winston-Salem By-pass Schedule Logic
SUMMARY | VARIANCE
VARIANCE SEPTEMBER 2019 | -363
VARIANCE JUNE 2020 | -151
TOTAL VARIANCE TO BE CLAIMED | 514 DAYS
Table (4) TOTAL VARIANCE TO BE CLAIMED :

## Slide 24
R-2247 EB Winston-Salem By-pass Schedule Logic
Conclusion
Blythe worked in good faith to recover the delays as far as they could by working out of sequence.
The TIA demonstrates that Blythe is entitled to excusable and compensable delay of 514 days due to delays beyond their control and requesting a compensable level of effort based on the cost per day agreed on.
PNG relocation was the controlling delay activity

## Slide 25
R-2247 EB Winston-Salem By-pass Schedule Logic
Critical Paths Before & After Impact

## Slide 26
R-2247 EB Winston-Salem By-pass Schedule Logic
Critical Paths Before & After Impact
Baseline Vs. sep 2019 impacted update

## Slide 27
R-2247 EB Winston-Salem By-pass Schedule Logic
Sep 2019 Update Critical Path Before Impact
VARIANCE = 0 CD delay

## Slide 28
R-2247 EB Winston-Salem By-pass Schedule Logic
Sep 2019 Critical Path Before Impact
VARIANCE = 0 CD delay

## Slide 29
R-2247 EB Winston-Salem By-pass Schedule Logic
Sep 2019 Critical Path Before Impact
VARIANCE = 0 CD delay

## Slide 30
R-2247 EB Winston-Salem By-pass Schedule Logic
Sep 2019 Critical Path After Impact
Updated Project Schedule Sep-2019
VARIANCE = -363 CD delay

## Slide 31
R-2247 EB Winston-Salem By-pass Schedule Logic
Sep 2019 Critical Path After Impact
Updated Project Schedule Sep-2019
VARIANCE = -363 CD delay

## Slide 32
R-2247 EB Winston-Salem By-pass Schedule Logic
Sep 2019 Critical Path After Impact
Updated Project Schedule Sep-2019
VARIANCE = -363 CD delay

## Slide 33
R-2247 EB Winston-Salem By-pass Schedule Logic
Critical Paths Before & After Impact
JUNE 2020 Vs. JUNE 2020 impacted update

## Slide 34
R-2247 EB Winston-Salem By-pass Schedule Logic
JUNE 2020 Critical Path Before Impact
Variance = -280 CD delay

## Slide 35
R-2247 EB Winston-Salem By-pass Schedule Logic
JUNE 2020 Critical Path Before Impact
Variance = -280 CD delay

## Slide 36
R-2247 EB Winston-Salem By-pass Schedule Logic
JUNE 2020 Critical Path Before Impact
Variance = -280 CD delay

## Slide 37
R-2247 EB Winston-Salem By-pass Schedule Logic
JUNE 2020 Critical Path AFTER Impact
Variance = -431 CD delay

## Slide 38
R-2247 EB Winston-Salem By-pass Schedule Logic
JUNE 2020 Critical Path AFTER Impact
Variance = -431 CD delay

## Slide 39
R-2247 EB Winston-Salem By-pass Schedule Logic
JUNE 2020 Critical Path AFTER Impact
Variance = -431 CD delay

## Slide 40
R-2247 EB Winston-Salem By-pass Schedule Logic
Critical Paths Before & After Impact
AUGUST 2020 Vs. AUGUST 2020 impacted update

## Slide 41
R-2247 EB Winston-Salem By-pass Schedule Logic
AUGUST 2020 Critical Path Before Impact
Variance = -259 CD delay

## Slide 42
R-2247 EB Winston-Salem By-pass Schedule Logic
AUGUST 2020 Critical Path Before Impact
Variance = -259 CD delay

## Slide 43
R-2247 EB Winston-Salem By-pass Schedule Logic
AUGUST 2020 Critical Path Before Impact
Variance = -259 CD delay

## Slide 44
R-2247 EB Winston-Salem By-pass Schedule Logic
AUGUST 2020 Critical Path AFTER Impact
Variance = -410 CD delay

## Slide 45
R-2247 EB Winston-Salem By-pass Schedule Logic
AUGUST 2020 Critical Path AFTER Impact
Variance = -410 CD delay

## Slide 46
R-2247 EB Winston-Salem By-pass Schedule Logic
AUGUST 2020 Critical Path AFTER Impact
Variance = -410 CD delay

## Slide 47: Project analysis slide 3
Review of Last Presentation
MARKET ANALYSIS
TECHNICAL ANALYSIS
FINANCIAL ANALYSIS
ECONOMIC ANALYSIS
ECOLOGICAL ANALYSIS
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY
Key Milestones and Contract Duration
Phasing
Technical Proposal – Recognition of Utility Conflicts
Technical Proposal - Considerations for Mitigation of PNG Conflict
Events Materially Affecting the Work
Contractual Basis of Claim
Cost Impact

## Slide 48: Project analysis slide 3
Key Milestones and Contract Duration
MARKET ANALYSIS
TECHNICAL ANALYSIS
FINANCIAL ANALYSIS
ECONOMIC ANALYSIS
ECOLOGICAL ANALYSIS
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY
$ 134,150,000
Date of Availability October 1, 2018
ICT 1 – Functional Interchange Date September 29, 2021
Substantial Completion August 3, 2022
Final Completion date September 1, 2022
Duration Including Design 1431 Calendar Days
Construction Duration 1089 Days
Review of Last Presentation

## Slide 49: Project analysis slide 3
Project Phasing
MARKET ANALYSIS
TECHNICAL ANALYSIS
ECONOMIC ANALYSIS
ECOLOGICAL ANALYSIS
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY
Review of Last Presentation
Phase 1 (US 52SB)
Phase 2 (US 52NB)
Phase 3 (Complete Interchange)

## Slide 50: Project analysis slide 3
Technical Proposal – Recognition of Utility Conflicts
MARKET ANALYSIS
TECHNICAL ANALYSIS
ECONOMIC ANALYSIS
ECOLOGICAL ANALYSIS
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY
Review of Last Presentation

## Slide 51: Project analysis slide 3
Technical Proposal – Considerations for Mitigation of PNG Conflict
MARKET ANALYSIS
TECHNICAL ANALYSIS
ECONOMIC ANALYSIS
ECOLOGICAL ANALYSIS
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY
Review of Last Presentation
Shifted US 52 SB horizontal alignment to the west and adjusted vertical profile to minimize fill over the transmission line and allow for US 52 SB crossing close to the cut-to-fill transition locations to be constructed independent from the relocation to the extent possible
Designed temporary US 52 SB alignment ties to minimize delays associated with relocation

## Slide 52: Project analysis slide 3
Events Materially Affecting the Work
MARKET ANALYSIS
TECHNICAL ANALYSIS
ECONOMIC ANALYSIS
ECOLOGICAL ANALYSIS
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY
Review of Last Presentation
  Delays
    Utilities (PNG relocation and Windstream most significant)
    Seasonal Weather Impact on Stabilization
    ROW (Map act & DOT Funding)
    Railroad
PNG relocation was the controlling delay activity

## Slide 53: Project analysis slide 3
Suspension
MARKET ANALYSIS
TECHNICAL ANALYSIS
ECONOMIC ANALYSIS
ECOLOGICAL ANALYSIS
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY
Review of Last Presentation
  When it became evident that Bridge 11 would not be completed as scheduled, Brian Webb recommended halting work with Wright Archer.
  The delay caused by PNG relocation was comparable to a work suspension.
  However, the Department of Transportation decided not to suspend work based on its own discretion and instead instructed the project to proceed.
  This decision led to an increase in overhead costs and resulted in the resequencing and inefficiencies of the work, which constituted a significant change in the nature of the work and its cost. Consequently, BCI issued a Notice of Intent to File a Claim under Section 104-3 of the Standard Specifications.

## Slide 54: Project analysis slide 3
Contractual Basis of Claim
MARKET ANALYSIS
TECHNICAL ANALYSIS
ECONOMIC ANALYSIS
ECOLOGICAL ANALYSIS
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY
Review of Last Presentation
Section 104-3 of the Standard Specifications
specifies that when a contractor is asked to perform work that, in their opinion, changes the plans or construction details in a way that significantly alters the nature of the work and its cost, they must inform the Engineer in writing before undertaking such work.

## Slide 55: Project analysis slide 3
Cost Impact
MARKET ANALYSIS
TECHNICAL ANALYSIS
ECONOMIC ANALYSIS
ECOLOGICAL ANALYSIS
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY
Review of Last Presentation
  The project experienced escalations due to market conditions, including significant delays and increased costs resulting from labor shortages and supply chain issues. These challenges were unprecedented and caused the project to be delayed by more than a year, exacerbating their effects.

## Slide 56: Project analysis slide 3
R-2247EB I-74 Interchange at US 52 NOI #1 Claim - Determination of Impact
MARKET ANALYSIS
TECHNICAL ANALYSIS
ECONOMIC ANALYSIS
ECOLOGICAL ANALYSIS
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY
Extended Indirect Cost
Annual Cost Increase (Escalations, Covid 19, Labor Shortage)
Annual Cost Increase (Escalations, Covid 19, Labor Shortage)
Inefficiencies Due to Work Sequencing of Structure 11
Cost Impact

## Slide 57: Project analysis slide 3
Existing Conditions Relative to Structure 11 Components
MARKET ANALYSIS
TECHNICAL ANALYSIS
ECONOMIC ANALYSIS
ECOLOGICAL ANALYSIS
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY
Streams/Wetland
Roadway Portion of Bridge Deck
Foundations
Structure Components Dependent on Fill and Stream
Relocation
PNG Line Effect on Fill and Stream Relocation
PNG Line Effect on Work Available
End Bent 1 /End Bent 2 Prior to the PNG Delay
End Bent 1 /End Bent 2 During the PNG Delay

## Slide 58: Project analysis slide 3
Existing Conditions Relative to Structure 11 Components
MARKET ANALYSIS
TECHNICAL ANALYSIS
ECONOMIC ANALYSIS
ECOLOGICAL ANALYSIS
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY
Streams/Wetland

## Slide 59: Project analysis slide 3
Existing Conditions Relative to Structure 11 Components
MARKET ANALYSIS
TECHNICAL ANALYSIS
ECONOMIC ANALYSIS
ECOLOGICAL ANALYSIS
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY
Roadway Portion of Bridge Deck

## Slide 60: Project analysis slide 3
Existing Conditions Relative to Structure 11 Components
MARKET ANALYSIS
TECHNICAL ANALYSIS
ECONOMIC ANALYSIS
ECOLOGICAL ANALYSIS
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY
Roadway Portion of Bridge Deck
SB US 52 Traffic Over New Structure 11

## Slide 61: Project analysis slide 3
Existing Conditions Relative to Structure 11 Components
MARKET ANALYSIS
TECHNICAL ANALYSIS
ECONOMIC ANALYSIS
ECOLOGICAL ANALYSIS
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY
Components Dependent on Fill and Stream Relocation

## Slide 62: Project analysis slide 3
Existing Conditions Relative to Structure 11 Components
MARKET ANALYSIS
TECHNICAL ANALYSIS
ECONOMIC ANALYSIS
ECOLOGICAL ANALYSIS
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY
PNG Line Effect on Fill and Stream Relocation

## Slide 63: Project analysis slide 3
Existing Conditions Relative to Structure 11 Components
MARKET ANALYSIS
TECHNICAL ANALYSIS
ECONOMIC ANALYSIS
ECOLOGICAL ANALYSIS
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY
PNG Line Effect on Work Available

## Slide 64: Project analysis slide 3
Direct Impact to Critical Path Through Structure 11
MARKET ANALYSIS
TECHNICAL ANALYSIS
ECONOMIC ANALYSIS
ECOLOGICAL ANALYSIS
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY
End Bent 1 /End Bent 2 Prior to the PNG Delay
End Bent 1 /End Bent 2 During the PNG Delay

## Slide 65
PNG Line Relocation
Stream Relocation
Y62 RMPC Mass Excavation
Construct End Bent 1A, 1B, 1C
Superstructure
Y62 RMPC Bottom Pipe
Mass Grading Bridge 11 Fills
Construct MSE Wall and End Bent 1
Construct MSE Wall and End Bent 2
Construct End Bent 2A, 2B, 2C
Set Girders, Structure 11
Direct Impact to Critical Path Through Structure 11
Note that End Bent 1 Work had been planned as concurrent with End Bent 2. Both end bents must be completed prior to setting girders and building superstructure.
End Bent 1 / End Bent 2 Prior to the PNG Delay
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY

## Slide 66
PNG Line Relocation
Stream Relocation EB2
Y62 RMPC Mass Excavation
Y62 RMPC Bottom Pipe
Mass Grading Bridge 11 Fills
Construct MSE Wall and End Bent 2
Construct MSE Wall and End Bent 1
Superstructure
Set Girders, Structure 11
Construct End Bent 2A, 2B, 2C
Construct End Bent 1A, 1B, 1C
Direct Impact to Critical Path Through Structure 11
Blythe Construction, Inc. pursued the work that could be done prior to PNG high pressure main relocation to our disadvantage, losing the efficiencies associated with building the end bents concurrently.
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY
End Bent 1 / End Bent 2 During to the PNG Delay
Note that End Bent 1 Work was not restrained by relocation of the PNG Gas Line. Since it had been planned as concurrent with End Bent 2, there was no critical path benefit gained from proceeding with it. Working End Bent 1 in advance had no bearing on the delay; it did not diminish the impact. Girders could not be set, nor superstructure built until End Bent 2 was completed.

## Slide 67: Project analysis slide 3
Determination of Impact
MARKET ANALYSIS
TECHNICAL ANALYSIS
ECONOMIC ANALYSIS
ECOLOGICAL ANALYSIS
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY
Basis of Determining Delay: Time Impact Analysis (TIA)
Key Points from ASCE Standard 67-17 Schedule Delay Analysis
Time Impact Analysis Methodology
Time Impact Analysis : Planned FIC and Substantial Completion
Time Impact Analysis : Impacted Function Interchange Completion
Time Impact Analysis : Impacted Substantial Completion

## Slide 68: Project analysis slide 3
Basis of Determining Delay: Time Impact Analysis (TIA)
MARKET ANALYSIS
TECHNICAL ANALYSIS
ECONOMIC ANALYSIS
ECOLOGICAL ANALYSIS
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY
  Industry standard method
  For this project, not a complex analysis
  Took CPM project schedule and removed all updated data to arrive at a baseline schedule for comparison
  Updated status through the actual relocation of PNG 8” high-pressure gas main (6/10/2020)
  Kept original durations, which eliminated any inefficiencies, regardless of which party caused them. This avoids the issue of DOT compensating for Blythe inefficiencies

## Slide 69: Project analysis slide 3
Key Points from ASCE Standard 67-17 Schedule Delay Analysis
MARKET ANALYSIS
TECHNICAL ANALYSIS
ECONOMIC ANALYSIS
ECOLOGICAL ANALYSIS
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY
Typical construction contracts require that delays be to critical path to justify a time extension.
The critical path may change during the course of the project.
Critical path method (CPM) techniques are the industry’s preferred practice for planning how to best complete a project. They are also extremely useful in determining the effects of delays and changes to the project.
Delay should generally be measured by the change to the scheduled completion date caused by the delay. Delay should generally be evaluated by comparing the schedules before, during, and after the event.
Examples of critical delay longer than the impacting event can include when the impacting event pushes the contractor into a constrained work period or requires reordering of long lead time materials.
The effects of a critical path delay also may affect the progress of work on noncritical paths.

## Slide 70: Project analysis slide 3
Time Impact Analysis Methodology
MARKET ANALYSIS
TECHNICAL ANALYSIS
ECONOMIC ANALYSIS
ECOLOGICAL ANALYSIS
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY
To prepare for a Time Impact Analysis, we removed all updates related to the progress of the project from the actual schedule being used for construction. This allowed us to establish the original Baseline Schedule while retaining the same activity durations. We then created the Impacted Schedule by updating actual dates up to the date when the PNG relocation was completed (June 10, 2020). This approach enabled us to eliminate any inefficiencies in our calculations, regardless of whether they were caused by Blythe or NCDOT. Ensuring accuracy and fairness in our analysis was a critical objective of the Time Impact Analysis methodology we utilized.

## Slide 71: Project analysis slide 3
Time Impact Analysis : Planned FIC and Substantial Completion
MARKET ANALYSIS
TECHNICAL ANALYSIS
ECONOMIC ANALYSIS
ECOLOGICAL ANALYSIS
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY
Substantial Completion

## Slide 72: Project analysis slide 3
Time Impact Analysis : Impacted Function Interchange Completion
MARKET ANALYSIS
TECHNICAL ANALYSIS
ECONOMIC ANALYSIS
ECOLOGICAL ANALYSIS
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY

## Slide 73: Project analysis slide 3
Time Impact Analysis : Impacted Substantial Completion
MARKET ANALYSIS
TECHNICAL ANALYSIS
ECONOMIC ANALYSIS
ECOLOGICAL ANALYSIS
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY

## Slide 74: Project analysis slide 3
Seasonal Ripple Effect Impact
MARKET ANALYSIS
TECHNICAL ANALYSIS
ECONOMIC ANALYSIS
ECOLOGICAL ANALYSIS
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY
120 Days vs. 90 Days
DOT Agreed Time Extension
Current DOT Position
Example of “Ripple Effect” of Seasonal Impact
“Ripple Effect” of Crossing Seasonal Impact Periods and Impact on Substantial Completion

## Slide 75: Project analysis slide 3
Seasonal (Climatological) Impact
120 Days vs. 90 Days
MARKET ANALYSIS
TECHNICAL ANALYSIS
ECONOMIC ANALYSIS
ECOLOGICAL ANALYSIS
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY
During discussions, the Department of Transportation (DOT) has indicated that the 120-day allowance for seasonal impact specified in the TIA is not permissible, as the DOT's seasonal limitation for granting time extensions is 90 days. It is important to note that the DOT's seasonal restriction does not address subgrade stabilization.
A responsible contractor would typically incorporate such time into their Critical Path Method (CPM) schedule as their experience indicates that it may affect certain operations, irrespective of whether the DOT recognizes it in the "seasonal limitation" language or not.
Based on our experience, stabilization efforts carried out before April 15 each year are usually ineffective due to normal temperatures and precipitation. Therefore, we included 120 days in our bid schedule for all winters, except the first, as minimal finish grading would be required during that period. It is imperative to highlight that the Department does not possess the authority within the contract language to eliminate any time that is included in our CPM schedule for any work.

## Slide 76: Project analysis slide 3
Seasonal (Climatological) Impact
Bid Schedule Plan for Seasonal Impact
MARKET ANALYSIS
TECHNICAL ANALYSIS
ECONOMIC ANALYSIS
ECOLOGICAL ANALYSIS
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY
DOT 90 Day Seasonal Limitation
Stabilization Duration Extended to Allow for Mar. 15 to Apr. 15 Lost productivity 90 Days
Reducing production rates to extend the work duration during the four weeks from March 15 to April 15 is considered a poor scheduling technique. The activity would have maintained the additional time even if it was rescheduled to a later period in the year when it would not be impacted by seasonal limitations.
DOT 90 Day Seasonal Limitation
Stabilization 60 Days
Stabilization Non-Work 30 Days
Based on our experience, stabilization efforts carried out before April 15 in any given year are typically ineffective due to normal temperatures and precipitation. As a result, we deemed it necessary to include a 120-day allowance in our bid schedule for all winters, except for the first, as minimal finish grading would be required during that period.
Bid Schedule Calendar-Based Allowance for Seasonal Impact 120 Days
Stabilization 60 Days
The appropriate approach to scheduling for this condition is to reflect actual conditions by incorporating non-workdays in the Critical Path Method (CPM) calendar for work that is impacted through April 15, rather than including them in the work activity itself. A Time Impact Analysis would provide the owner with the advantage of any time savings that may result from missing the seasonal impact period.
Dec. 15
Mar. 15
Apr.15
Jun.15

## Slide 77: Project analysis slide 3
Seasonal (Climatological) Impact
DOT Agreed Time Extension
MARKET ANALYSIS
TECHNICAL ANALYSIS
ECONOMIC ANALYSIS
ECOLOGICAL ANALYSIS
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY
The Department of Transportation (DOT) has suggested awarding a duration of 282 days (plus or minus) for the PNG delay period. However, this timeframe is insufficient for adequately compensating for the actual schedule impact. It only accounts for the 277-day delay to the start of the work associated with ICT 1, along with an additional 5 days of impact to the FIC (totaling 282 days) and a further 3-day delay to Substantial Completion (totaling 285 days).
If the delay had been precisely one year, it might have resulted in a day-for-day shift of the FIC and Substantial Completion, as proposed by NCDOT. A schematic outlining how this would work is provided below.

## Slide 78: Project analysis slide 3
Magnitude of Impact
Current DOT Position
MARKET ANALYSIS
TECHNICAL ANALYSIS
ECONOMIC ANALYSIS
ECOLOGICAL ANALYSIS
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY
The current stance of the Department of Transportation (DOT) appears to suggest that the impact of the PNG delay did not affect work that came after the PNG relocation ended. Therefore, only a delay of 285 days is deemed necessary. The illustration on the right demonstrates this line of reasoning.
277 Days Delay

## Slide 79: Project analysis slide 3
1 Year Suspension or Delay
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY
If the delay had been exactly 1 year, it might have resulted in a day for day shift of the FIC and Substantial Completion as proposed by NCDOT in the prior slide, as shown below.
Seasonally Affected Work
Non-Seasonally Affected Work
No Additional Climate Impact
Net Increase in Duration - Time Extension Only
Winter
Winter
Winter
Winter
Suspension – No Indirect Cost Due to Demobilization
Winter
Winter
Winter
2019
2020
2021
2019
2020
2021

## Slide 80: Project analysis slide 3
Example of “Ripple Effect” of Seasonal Impact
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY
However, as a result of the partial year shift, activities that were not initially impacted by seasonal conditions became affected, resulting in additional days being added to the critical path. It is important to note that since our Time Impact Analysis is based on our Critical Path Method (CPM) schedule, and not a simple bar chart, the scheduling logic drives the calculation of the impact.
To rephrase, our Time Impact Analysis (TIA) is not focused on obtaining a general extension for an additional winter period. We have not requested a broad "seasonal limitation" that covers a specific range of dates, but rather the precise impact of seasonal conditions on activities such as stabilization, only to the extent that it has affected the critical path of the project.
Winter
Winter
Winter
Winter
Seasonally Affected Work
Non-Seasonally Affected Work
Initial Delay to Schedule
Reductions to Climate Impact
Net Increase in Duration
Climate Impact to Schedule
Planned (Baseline)
Climate Impact
Initial PNG Delay
Net Impact to Project
Initial PNG Relocation Delay
Winter
Winter
2019
2020
2021
2019
2020
2021

## Slide 81: Project analysis slide 3
Magnitude of Impact
“Ripple-Effect” of Seasonal Impact
MARKET ANALYSIS
TECHNICAL ANALYSIS
ECONOMIC ANALYSIS
ECOLOGICAL ANALYSIS
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY
After analyzing the Critical Path Method (CPM) schedule, it has become apparent that a delay to Structure 11 will result in key milestones on the critical path that follows it being delayed. This impact will increase over time due to the need to carry out cold and wet weather-sensitive work during a seasonal period when it cannot be performed.
Furthermore, a delay that pushes climate-sensitive work into a single winter period can result in work gaps that push other tasks into the winter season, which were not initially scheduled to be carried out during that time.
An example of how this delay has affected the project schedule is illustrated in the next slide.

## Slide 82: Project analysis slide 3
Seasonal Impact
“Ripple Effect” of Crossing Seasonal Impact Periods and Impact on Substantial Completion
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY
Grading & Road Work
Grading & Road Work
Grading & Road Work
Non-Seasonally Affected Work
Seasonally Affected Work
Grading & Road Work
“Ripple Effect” of Crossing Seasonal Impact Periods
PNG Relo. Delay 277 Days
Substantial Completion 417 Days
FIC (ICT #1) 330 Days
Substantial Completion
430 Days

## Slide 83: Project analysis slide 3
Magnitude of Impact
Large Magnitude Delay of the Critical Path
MARKET ANALYSIS
TECHNICAL ANALYSIS
ECONOMIC ANALYSIS
ECOLOGICAL ANALYSIS
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY
As a result of the interchange phasing restriction, the project construction team had no viable options to mitigate this delay, other than for the Department of Transportation (DOT) to suspend the work until the relocation of PNG (and other critical utilities) had been completed. Completion of Structure 11 was a crucial prerequisite for progressing to the next phase of the project. Therefore, it is logical to expect that such a delay would follow through the critical path and potentially increase in magnitude as subsequent winter seasons were crossed, as has been demonstrated.
This delay had a significant impact on the critical path of the project, resulting in a substantial increase in magnitude.

## Slide 84: Project analysis slide 3
Seasonal (Climatological) Impact
MARKET ANALYSIS
TECHNICAL ANALYSIS
ECONOMIC ANALYSIS
ECOLOGICAL ANALYSIS
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua.
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY
It is crucial to note that ICT 1 (Functional Interchange Completion) is just one component of the overall project. The majority of the work that was scheduled after the relocation of PNG and was also scheduled after ICT #1 (FIC) could not be re-sequenced to be performed before FIC. This was primarily due to the Traffic Management Plan and its impact on the availability of areas to work. As a result, to a significant extent, a delay to the FIC resulted in a delay to Substantial Completion, as the delay propagated through the critical path.

## Slide 85: Project Phasing
Phase 1 (US 52SB)
Phase 2 (US 52NB)
Phase 3 (Complete Interchange)
Review of Last Presentation

## Slide 86
Ripple Effect Impact

## Slide 87
Ripple Effect Impact

## Slide 88
Ripple Effect Impact

## Slide 89
Ripple Effect Impact

## Slide 90: - Magnitude of PNG Relocation Impact - Functional Interchange Completion - Substantial Completion - Summary
R-2247 EB Winston-Salem Northern Beltway Interchange at US 52 FOR SETTLEMENT PURPOSES ONLY
Magnitude of Impact

## Slide 91: If there is a significant delay to the critical path of any project, a delay of the magnitude of 36.8% of the available time would be extremely challenging to overcome, unless there is a way to modify the critical tasks through a major schedule revision.
36.8% of Construction Time Lost
277 DAYS
Large Magnitude Delay of the Critical Path
NCDOT Objections to Settlement

## Slide 92: Percent of FIC Construction Days Lost Due to PNG delay
Planned Construction Days from PNG Relocation
to ICT #1 Functional Interchange Open: 752 Days
Days of Delay in PNG Relocation: 277 Days
36.8 % of planned construction days lost from project critical path = a total change of sequence and work plan forced on Blythe by not suspending work until PNG relocation was completed. It was impossible to recover a loss of 36.8%
Magnitude of Impact

## Slide 93: Magnitude of Delay to Functional Interchange Completion
Planned Construction Days from Project Start to ICT #1 Planned Functional Interchange Completion (Baseline): 751 Days
Total days to Functional Interchange Completion: 1182 Days
Net Additional Days to Function Interchg. Compl.: 430 Days
Adding 57.3 % of planned (baseline) days
to Functional Interchange Completion
Magnitude of Impact

## Slide 94: Magnitude of Delay to Substantial Completion
Planned Construction Days from Project Start to Substantial Completion: 1060 Days
Days to Achievement of Substantial Completion: 1477 Days
Net Additional Days to Substantial Completion: 417 Days
Adding 39.34 % of planned (baseline) days to Substantial Completion
Magnitude of Impact

## Slide 95: Summary of Magnitude of Impact
Description | Days | % of Impact
Loss of Planned Construction Days from PNG Relocation to ICT #1 Functional Interchange Completion | 277 of 752 days | 36.8 %
Impact on Functional Interchange Date | 430 added to 751 days | 57.3 %
Impact on Substantial Completion Date | 417 days added to 1060 | 39.3 %
Magnitude of Impact

## Slide 96
A Time Impact Analysis (TIA), the method chosen to determine schedule impact for this claim, is the industry standard method
Our determination of days due is a logical, scientific approach
We used the March 20, 2020 actual schedule as a basis for our Baseline and Impacted schedules, keeping the planned activity durations. This was appropriate, removing the “bias” that would have occurred if we had used actual durations instead of planned durations.
While we may disagree, we would welcome discussion of Division 9 objections to many of the days requested, if the objections are based on an approach that meets industry standards and good scheduling practice
Summary

## Slide 97: Thank You
Questions & Answers

## Slide 98
Ripple Effect Impact

## Slide 99
Ripple Effect Impact

## Slide 100
Ripple Effect Impact

## Slide 101
Ripple Effect Impact

## Slide 102
Ripple Effect Impact

## Slide 103
Ripple Effect Impact

## Slide 104
Ripple Effect Impact

## Slide 105
Ripple Effect Impact

## Slide 106: Thank You
Thank You